## Instructions
Workbook Instructions This workbook is to be completed and attached to your Sustainable Communities Challenge Fund (the Fund) application. Before attaching the completed workbook, please rename it to that of your organization for identification purposes. Also, please ensure that the total eligible project costs requested in the workbook match the amount in your application. Sections that are highlighted blue are locked and do not need to be edited. If the cell is white, you may edit this section. Before continuing please fill in the following:
Lead Applicant | Municipality of ABC Example
Project Title | Powering Community Resilience
Project Start Date | 2026-11-30
Project End Date | 2027-11-01
Please contact the Fund team at info@sccfns.ca if you require any assistance completing the worksheets. This workbook contains:
1. Project Milestones and Timelines (Sheet 3) - This sheet contains a template to outline project milestones, specific activities tied to each milestone and their duration. For each milestone, demonstrate measurable outcomes that will be used to assess the project's success. In the 'Completed-by" column give an indication as to who will be completing the presented activity, for example activity #1 will be completed by the SCCF Grant Coordinator.
2. Milestone 1 - 6 (Sheet 4 - 9) - You will be required to breakdown your project into its main milestones (up to a maximum of 6). These 6 milestones can be comprised of many activities that you will outline in the "Project Milestones & Timelines" sheet; each milestone should have at least 1 associated activity. On the milestone sheets you will provide a breakdown of your milestone budgets by providing short descriptions of the budget lines, as well as indicating if the budget will be covered by cash or in-kind. A reminder that funding decisions will not be made until the Fall of 2026, and projects are required to finish by November 30, 2027. Any costs incurred before a singed funding agreement is provided by NSFM will not be considered eligible.
3. Sources of Funding (Sheet 10)- Outline the various sources of funding you will be using to fund this project, indicate if they are confirmed, and the amount of each source. If you do not require the total amount of funding you are eligible for under the Fund, you are able to request a lesser amount. In order to do so enter the lesser amount on the sources of funding page in the pre-populated section for the Sustainable Communities Challenge Fund's funding source. Once you enter a lesser amount you will find a revised funding breakdown on the "Project Overview" sheet.
4. Project Overview (Sheet 11) - This sheet contains all of the information on your project that you have entered on the previous sheets. It will provide a breakdown of your eligible funding request from the Fund and how much contribution is required by your organization in cash, as well as your optional in-kind contribution. Grants provided from the Sustainable Communities Challenge Fund are considered provincial funds. As per the stacking rules for the Fund (see Applicant Guide), it is important to note that no more than 80% of the total eligible project costs can be covered by the Province of Nova Scotia. Based on the information you enter in your sources of funding sheet, the workbook will indicate whether or not you are exceeding the provincial funding maximum of 80%. The expenditures by milestone chart will give you a breakdown of the cost of each individual milestone associated with your project. The expenditures by cost category chart provides a breakdown of your budget into each individual cost category.

## Eligible and Ineligible Costs
Eligible Costs | Ineligible Costs
Accessibility Supports: These expenses cover items or services that ensure accessibility for individuals with disabilities. This could include sign language interpreters, braille materials, or assistive technology. | Existing employment or operating costs that are already established as part of the funding recipient’s organizational budget.
Equipment Rental: This category includes the cost of renting or leasing equipment necessary for the project. Examples could be renting heavy machinery for construction, audiovisual equipment for an event, or specialized tools for a research project. | Costs for services or work normally provided by the funding recipient, incurred over the course of implementing the project, except those specified as eligible expenditures.
Professional Services: These expenses involve fees paid to external professionals or consultants who provide specialized expertise or services to the project. Examples include legal fees, consulting fees, fees for graphic design and marketing services, or costs associated with hiring someone to conduct a GHG quantification report for the project. Consulting costs (up to $5,000) for preparing the project application, incurred up to 60 days before the application submission, are eligible (note that staff salaries to prepare the application are not eligible for reimbursement). | Costs associated with operating expenses and regularly scheduled maintenance work.
Staff Remuneration: This category covers the salaries, wages, and benefits of project team members or employees. This does not include regular staff salaries, but rather the amount that is directly associated with the proposed project. If including existing staff, demonstrate their contribution in hours and associated costs; this applies to new staff as well. | Initiatives that need to be undertaken as a result of federal or provincial regulation/legislation.
Supplies and Materials: These costs pertain to the purchase of tangible items and materials needed for the project. This can encompass office supplies, construction materials, laboratory supplies, or any materials directly related to project activities. | Purchase or leasing of property, including land, buildings, and/or other facilities.
Travel, Accommodation, and Facility Rental: These expenses are associated with traveling to project-related events or locations. It includes costs for transportation, accommodation (such as hotels), rental of meeting or event facilities and hosting community gatherings related to project activities. | Real estate fees and related costs.
Permit Fees: This category includes fees required for obtaining necessary permits or licenses to carry out the project. This can include building permits, environmental permits, or any other legal authorizations needed. | Financing charges, legal fees, and loan interest payments, including those related to easements (e.g., surveys).
Miscellaneous Expenses: This category is reserved for budget items that do not fit neatly into the predefined categories but are essential for the project. | Costs for materials, supplies, transportation, or services other than those directly related to the implementation of the project
Costs for furnishings and non-fixed assets which are not essential for the operation of the asset / project.
Any Goods and Services Tax (GST) / Harmonized Sales Tax (HST) that is reimbursable by the Canada Revenue Agency and any Provincial Sales Tax that is reimbursable by the Province.
Costs incurred for rejected, withdrawn, or cancelled projects.

## Project Milestones & Timelines
Project Milestones and Timelines
Community Engagement | 2026-09-01 | 2027-02-01
Description | Activities | Timeline (Start / End Date) |  | Completed By
Hire facilitator | Hire a facilitator for the engagement sessions | 2026-09-01 | 2026-10-12 | Project Manager
Pre-engagement preparation | Includes: Preparing materials for the session, creating a webpage for invitees to reference, scheduling times and locations, creating and sending out invitations, create medium to capture input | 2026-10-15 | 2027-02-01 | Project Manager
Hosting Sessions | Includes: 3 facilitated in-person sessions, 1 online recorded session, online survey. | 2026-10-15 | 2027-02-01 | Project Manager
Prepare Findings | Includes: synthesizing input captured from engagement sessions, writing an executive summary report, and presenting recommendation for next steps to leadership. | 2026-10-15 | 2027-02-01 | Project Manager
Select project location | Includes: obtaining sign-off from leadership, announce the selected location publicly. | 2026-10-15 | 2027-02-01 | Project Manager
Technical Design & Permitting | 2027-03-12 | 2027-06-16
Description | Activities | Timeline (Start / End Date) |  | Completed By
Hire Professional Services | Includes: defining technical requirements, conduct a physical site assessment/survey, geotechnical assessment, preparing detailed designs, preparing tenders for procurement | 2027-03-12 | 2027-04-14 | Project Manager
Obtain Permits | Includes: proof of land ownership, any building permits (if required), NSPI review of drawings | 2027-04-17 | 2027-06-16 | ABC Consulting
Procurement | Includes: purchasing equipment, solar panels, battery storage. | 2027-04-17 | 2027-06-16 | ABC Consulting
Construction | 2027-06-19 | 2027-11-30
Description | Activities | Timeline (Start / End Date) |  | Completed By
Site Preparation | Includes: Clear site, prepare site for ground mount installation, consider/apply climate adaptation measures. *Please note, we've provided a buffer between procurement and construction to account for the winter season. Construction will begin in the Spring. | 2027-06-19 | 2027-06-27 | ABC Consulting
Installation | Includes: Installation of the racking, the solar panels and battery storage | 2027-06-30 | 2027-09-28 | ABC Consulting
Electrical Inspection | Includes: Final NSPI electrical inspection | 2027-11-25 | 2027-11-30 | NS Power
Milestone #4 (Replace with Title) | Start Date (Replace with Start Date) | End Date (Replace with End Date)
Description | Activities | Timeline (Start / End Date) |  | Completed By
Milestone #5 (Replace with Title) | Start Date (Replace with Start Date) | End Date (Replace with End Date)
Description | Activities | Timeline (Start / End Date) |  | Completed By
Milestone #6 (Replace with Title) | Start Date (Replace with Start Date) | End Date (Replace with End Date)
Description | Activities | Timeline (Start / End Date) |  | Completed By

## Milestone 1
Lead Applicant: | Municipality of ABC Example
Project Title: | Powering Community Resilience
Project Start Date: | 2026-11-30
Project End Date: | 2027-11-01
Community Engagement
2026-09-01 |  | 2027-02-01
Cost Category | Description Please provide a brief description of the expense. For example: Equipment Rental - Pedestrian Counters Equipment for Trail Usage Tracking. | In Kind ($) | Cash ($) | Total ($)
Accessibility Supports: | Translation for public facing materials |  | 1500 | 1500
Equipment Rental: |  |  |  | 0
Professional Services: | Facilitator for Community Engagement Sessions |  | 20000 | 20000
Staff Remuneration: |  |  |  | 0
Supplies and Materials: | Printed Material, IT and web-based software/platforms |  | 1000 | 1000
Travel, Accomodation, and Facility Rental: | In-kind facility rental, travel for engagement sessions. | 2000 | 500 | 2500
Permit Fees: |  |  |  | 0
Miscellaneous Expenses: | Contingency |  | 2500 | 2500
| Total | 2000 | 25500 | 27500

## Milestone 2
Lead Applicant: | Municipality of ABC Example
Project Title: | Powering Community Resilience
Project Start Date: | 2026-11-30
Project End Date: | 2027-11-01
Technical Design & Permitting
2027-03-12 |  | 2027-06-16
Cost Category | Description Please provide a brief description of the expense. For example: Equipment Rental - Pedestrian Counters Equipment for Trail Usage Tracking. | In Kind ($) | Cash ($) | Total ($)
Accessibility Supports: |  |  |  | 0
Equipment Rental: |  |  |  | 0
Professional Services: | Engineering Services |  | 20000 | 20000
Staff Remuneration: |  |  |  | 0
Supplies and Materials: | Procurement of equipment (quote provided) |  | 250000 | 250000
Travel, Accomodation, and Facility Rental: | Travel to site for assessments/surveys |  | 500 | 500
Permit Fees: | Application fees for interconnection |  | 3000 | 3000
Miscellaneous Expenses: | Contingency |  | 28650 | 28650
| Total | 0 | 302150 | 302150

## Milestone 3
Lead Applicant: | Municipality of ABC Example
Project Title: | Powering Community Resilience
Project Start Date: | 2026-11-30
Project End Date: | 2027-11-01
Construction
2027-06-19 |  | 2027-11-30
Cost Category | Description Please provide a brief description of the expense. For example: Equipment Rental - Pedestrian Counters Equipment for Trail Usage Tracking. | In Kind ($) | Cash ($) | Total ($)
Accessibility Supports: |  |  |  | 0
Equipment Rental: |  |  |  | 0
Professional Services: | Installation and site preparation |  | 50000 | 50000
Staff Remuneration: |  |  |  | 0
Supplies and Materials: |  |  |  | 0
Travel, Accomodation, and Facility Rental: | Travel to site |  | 500 | 500
Permit Fees: | Final electrical inspection |  | 1000 | 1000
Miscellaneous Expenses: | Contingency |  | 5150 | 5150
| Total | 0 | 56650 | 56650

## Milestone 4
Lead Applicant: | Municipality of ABC Example
Project Title: | Powering Community Resilience
Project Start Date: | 2026-11-30
Project End Date: | 2027-11-01
Milestone #4 Title
Milestone Start Date: |  | Milestone End Date:
Cost Category | Description Please provide a brief description of the expense. For example: Equipment Rental - Pedestrian Counters Equipment for Trail Usage Tracking. | In Kind ($) | Cash ($) | Total ($)
Accessibility Supports: |  |  |  | 0
Equipment Rental: |  |  |  | 0
Professional Services: |  |  |  | 0
Staff Remuneration: |  |  |  | 0
Supplies and Materials: |  |  |  | 0
Travel, Accomodation, and Facility Rental: |  |  |  | 0
Permit Fees: |  |  |  | 0
Miscellaneous Expenses: |  |  |  | 0
| Total | 0 | 0 | 0

## Milestone 5
Lead Applicant: | Municipality of ABC Example
Project Title: | Powering Community Resilience
Project Start Date: | 2026-11-30
Project End Date: | 2027-11-01
Milestone #5 Title
Milestone Start Date: |  | Milestone End Date:
Cost Category | Description Please provide a brief description of the expense. For example: Equipment Rental - Pedestrian Counters Equipment for Trail Usage Tracking. | In Kind ($) | Cash ($) | Total ($)
Accessibility Supports: |  |  |  | 0
Equipment Rental: |  |  |  | 0
Professional Services: |  |  |  | 0
Staff Remuneration: |  |  |  | 0
Supplies and Materials: |  |  |  | 0
Travel, Accomodation, and Facility Rental: |  |  |  | 0
Permit Fees: |  |  |  | 0
Miscellaneous Expenses: |  |  |  | 0
| Total | 0 | 0 | 0

## Milestone 6
Lead Applicant: | Municipality of ABC Example
Project Title: | Powering Community Resilience
Project Start Date: | 2026-11-30
Project End Date: | 2027-11-01
Milestone #6 Title
Milestone Start Date: |  | Milestone End Date:
Cost Category | Description Please provide a brief description of the expense. For example: Equipment Rental - Pedestrian Counters Equipment for Trail Usage Tracking. | In Kind ($) | Cash ($) | Total ($)
Accessibility Supports: |  |  |  | 0
Equipment Rental: |  |  |  | 0
Professional Services: |  |  |  | 0
Staff Remuneration: |  |  |  | 0
Supplies and Materials: |  |  |  | 0
Travel, Accomodation, and Facility Rental: |  |  |  | 0
Permit Fees: |  |  |  | 0
Miscellaneous Expenses: |  |  |  | 0
| Total | 0 | 0 | 0

## AB Total (hidden)
Awareness Building Activity
Activity | Start date | End date | Eligible Expenditures ($) | Ineligible Expenditures ($) | Total Expenditure ($)
All Activities Phase 1 | 01/Jan/2020 | 30/Jun/2020
All Activities Phase 1 - Total |  |  | #REF! | #REF! | #REF!
All Activities Phase 2 | 01/Jul/2020 | 31/Dec/2020
All Activities Phase 2 - Total |  |  | #REF! | #REF! | #REF!
All Activities Phase 3 | 01/Jan/2021 | 3/Jun/2021
All Activities Phase 3 - Total |  |  | #REF! | #REF! | #REF!
Total Expenditures |  |  | #REF! | #REF! | #REF!
|  | Total Eligible Expenditures |  |  | #REF!

## TA Total (hidden)
Technical Assistance Activity
Program | Start date | End date | Eligible Expenditures ($) | Ineligible Expenditures ($) | Total Expenditure ($)
All Programs Phase 1 | 01/Jan/2020 | 30/Jun/2020
All Programs Phase 1 - Total |  |  | #REF! | #REF! | #REF!
All Programs Phase 2 | 01/Jul/2020 | 31/Dec/2020
All Programs Phase 2 - Total |  |  | #REF! | #REF! | #REF!
All Programs Phase 3 | 01/Jan/2021 | 3/Jun/2021
All Programs Phase 3 - Total |  |  | #REF! | #REF! | #REF!
Total Expenditures |  |  | #REF! | #REF! | #REF!
|  | Total Eligible Expenditures |  |  | #REF!

## Sources of Funding
Sources of Funding
Please reflect your total eligible budgets sources of funding below, the amount should total: $386,300.00
Funder's Name | Description | In-kind/Cash | Have you received confirmation of these matching funds? (Y/N) | Date Committed DD-MM-YYYY | Amount ($) | % of Funding
Sustainable Communities Challenge Fund | Provincial | Cash | No | TBD | 270000 | 69.89%
Municipality of ABC Example | Other (Describe) | In-kind | Yes | 01-11-2023 | 2000 | 0.5177%
Municipality of ABC Example | Other (Describe) | Cash | No | 01-03-2024 | 77260 | 20%
ACOA - Innovative Communities Fund | Federal | Cash | No | 19-01-2024 | 37040 | 9.588%
0%
0%
|  |  |  | Total Funding: | 386300 | 100%
|  |  |  | Required Contribution: | 386300
|  |  |  | Contribution Still Required: | 0
If you selected "Other" as a funding description, please explain below: You may also use the notes section to provide any details about your sources of funding you think may be important.
Notes: | In-kind facility rental ($2,000)
Notes: | Municipal cash contribution ($77,260)
Notes:
Notes:

## Project Overview
Project Overview
Lead Applicant: | Municipality of ABC Example
Project Title: | Powering Community Resilience
Start Date: | 2026-11-30
End Date: | 2027-11-01
Funding Overview | Eligible Maximums | Applicants Request (Subject to Program Review)
Sustainable Communities Challenge Fund Request ($) | 270410 | 270000
Applicant's Required Contribution | 115890 | 116300
Minimum Cash Contribution | 77260 | 77670
Optional In-kind Contribution (Max 10%) | 38630 | 38630
Total | 386300 | 386300
Total Provincial Funding | Eligible / Not Eligible
69.89% | Eligible
Expenditures by Milestone
Milestone Name | Total Eligible Expenditures
Milestone 1:Community Engagement | 27500
Milestone 2:Technical Design & Permitting | 302150
Milestone 3:Construction | 56650
Milestone 4:Milestone #4 Title | 0
Milestone 5:Milestone #5 Title | 0
Milestone 6:Milestone #6 Title | 0
Total | 386300
Expenditures by Cost Category
Cost Category | Total Eligible Expenditures
Accessibility Supports | 1500
Equipment Rental | 0
Professional Services | 90000
Staff Remuneration | 0
Supplies and Materials | 251000
Travel, Accommodation, and Facility Rental | 3500
Permit Fees | 4000
Miscellaneous Expenses | 36300
Total | 386300